## BOQ
ASTER COURTYARD RESIDENCE | [5 empty] | PROJECT SNAPSHOT
Bill of quantities / Illustrative project | [5 empty] | Direct works budget
Original sample data ¦ All amounts in INR ¦ Rev 01 | [5 empty] | 62.285
Item | Description | Quantity | Unit | Rate (INR) | Amount (INR) | Work package | Budget (INR)
01 EARTHWORK | [5 empty] | Earthwork | 288000
1.1 | Site clearing | 500 | m2 | 120 | 60000 | Concrete | 2829000
1.2 | Foundation excavation | 320 | m3 | 450 | 144000 | Masonry | 867500
1.3 | Backfilling & compaction | 280 | m3 | 300 | 84000 | Finishes | 1399000
02 CONCRETE WORKS | [5 empty] | Services | 845000
2.1 | PCC foundation bed | 150 | m3 | 6500 | 975000
2.2 | Reinforced concrete | 220 | m3 | 7200 | 1584000
2.3 | Formwork to structure | 600 | m2 | 450 | 270000
03 MASONRY
3.1 | External brickwork | 850 | m2 | 650 | 552500
3.2 | Internal blockwork | 420 | m2 | 750 | 315000
04 FINISHES
4.1 | Internal wall plaster | 1800 | m2 | 240 | 432000
4.2 | Flooring & skirting | 620 | m2 | 950 | 589000
4.3 | Wall & ceiling paint | 2100 | m2 | 180 | 378000
05 BUILDING SERVICES
5.1 | Electrical installation | 1 | item | 480000 | 480000
5.2 | Plumbing installation | 1 | item | 365000 | 365000
| Direct works subtotal |  |  |  | 6228500
| Contingency allowance |  |  | 5% | 311425
| Subtotal incl. contingency |  |  |  | 6539925 | 13 measured items / 5 work packages
| Illustrative GST |  |  | 18% | 1177186.5 | Live formulas connect quantities to totals.
| PROJECT TOTAL |  |  |  | 7717111.5
Sample only: verify quantities, local rates and taxes for your own project.

## Cost Dashboard
Aster Courtyard / Cost dashboard
Illustrative project controls ¦ Linked to the BOQ worksheet
DIRECT WORKS |  |  | TOTAL INCL. ALLOWANCES & SAMPLE TAX
62.285 |  |  | 77.1711
Work package | Budget (INR) | Share | Month | Planned (INR) | Actual (INR)
Earthwork | 288000 | 4.624% | Jan | 450000 | 420000
Concrete | 2829000 | 45.42% | Feb | 750000 | 710000
Masonry | 867500 | 13.93% | Mar | 1100000 | 1025000
Finishes | 1399000 | 22.46% | Apr | 1350000 | 1280000
Services | 845000 | 13.57% | May | 1500000 | 1465000
|  |  | Jun | 1078500 | 1010000
Invented rates and progress values for demonstration. Not market prices or tax advice.